## SAMPLE 2 - WFP
NATIONAL INNOVATION COUNCIL
FY 2022 INNOVATION GRANTS
FORM 3A: Project Work and Financial Plan FY 2022
Program/Project Title: | Innovation Facilitators Training and Cascading Workshops
Department/Agency: | Department of the Interior and Local Government (DILG)
Implementing Entity: | DOST-Local Government Academy (LGA)
Implementation Period: | July to December 2022
Proposed Budget: | PHP 1,386,000.00
Objective Statement: | To promote innovation and capacitate local leaders with creative and design thinking that will be integral in pursuing innovative solutions to community problems
Work Plan |  |  |  |  | Physical Accomplishment | [6 empty] | Financial Targets
Specific Objectives | Outcome Indicator | Activities | Success Measures/KPIs | Responsible Unit | Target | Timeline | [5 empty] | Resource Requirement
[6 empty] | Q3 |  |  | Q4 |  |  | Item/s Description | Type of Expense | Targeted Release (month) | ESTIMATED COST
[6 empty] | JUL | AUG | SEP | OCT | NOV | DEC |  |  |  | UNIT ESTIMATE | QTY | SUB-TOTAL
Specific Objective 1: To develop a pool of specialized Filipino trainers/professionals/practitioners who have both the knowledge and skills to develop and promote innovation and creative thinking in their respective fields and communities | Increase in the number of facilitators who can be tapped to help cascade and train others to develop and promote innovation and creative thinking | 1.1 Call for Applicants | No. of applications received and acknowledged | TBD | 20 applications | Q3 JUL: Call for Applicants | N/A | N/A | N/A | 0 | 0 | 0
|  | 1.2 Deliberation and Approval of Applicants | No. of applicants deliberated |  | 20 applications | Q3 AUG: Deliberation & Approval of Applicants | Snacks & Lunch of Deliberation Panel and Secretariat | Other Maintenance and Operating Expenses - Representation Expenses | Aug | 3000 | 2 | 6000
|  | 1.3 Attendance to Local/Foreign Innovation & Design Thinking Facilitator Program | No. of delegates who successfully completed the facilitator program | TBD | 10 delegates | Q3 AUG: Conduct of Local/Foreign Innovation & Design Thinking Facilitator Program | Round-Trip Air/Land/Boat Fare for 10 persons | Training and Scholarship Expenses - Training Expenses | Aug | 15000 | 10 | 150000
[12 empty] | Accommodation for 30 days |  | Aug | 30000 | 10 | 300000
[12 empty] | Living Allowance for 30 days |  | Aug | 40000 | 10 | 400000
|  | 1.4 Implementation of Re-entry/Cascading Plan | No. of re-entry/cascading plans implemented | TBD | 10 plans | Q3 SEP: Start of Implementation of Re-entry/Cascading Plans; Q4 DEC: Writing and Submission of Accomplishment Reports | N/A | N/A | N/A | 0 | 0 | 0
Specific Objective 2: To train and capacitate personnel in local development units with design thinking and innovation that can be applied in creating new solutions to their communities | Increase in the number of personnel in the local level who are skilled with design thinking and is pursuing innovative solutions to local challenges | 2.1 Procurement of Office and ICT Equipement and Project Supplies and Materials | No. of equipment, supplies and materials procured | TBD | 2 procurement activities | Q3 AUG: Procurement of Project Supplies & Materials; Q3 SEP: Procurement of Project Supplies & Materials | Bond Paper, Toner Cartridge, Stapler, Staple Wire, Puncher, Pens, Folders, Envelopes, etc. | Supplies and Materials Expenses - Office Supplies Expenses | Aug to Sep | 30000 | 1 | 30000
[12 empty] | Laser Printer | Machinery and Equipment - Information and Communications Technology Equipment |  | 20000 | 1 | 20000
|  | 2.2 Field Work/Visits to Target Stakeholders | No. of activities conducted | TBD | 10 activities | Q4 OCT: 5 Field Work/Visits; Q4 NOV: 5 Field Work/Visits | Round-Trip Air/Land/Boat Fare for 10 persons | Training and Scholarship Expenses - Training Expenses | Oct to Nov | 10000 | 1 | 10000
[12 empty] | Accommodation for 5 days |  |  | 7000 | 10 | 70000
|  | 2.3 Conduct of Innovation and Design Thinking Workshop to Local Communities | No. of workshops conducted | TBD | 10 workshops | Q4 OCT: 5 Field Workshops; Q4 NOV: 5 Field Workshops | Rent/Lease of Venue | Training and Scholarship Expenses - Training Expenses | Oct to Nov | 15000 | 10 | 150000
[12 empty] | Snacks and Lunch for Participants |  |  | 25000 | 10 | 250000
[15 empty] | TOTAL |  | 1386000
Prepared By: | Recommending Approval: | Approved By:
___________________________ | ___________________________ | ___________________________
Kathryn Padilla, Technical Specialist | Nora Santos, Director | Gary Nievera, Undersecretary
2022-01-01 | 2022-01-02 | 2022-01-03

## SAMPLE 2 - LIB
NATIONAL INNOVATION COUNCIL
FY 2022 INNOVATION GRANTS
FORM 3B: Project Line-Item Budget
Program/Project Title |  |  | : | Innovation Facilitators Training and Cascading Workshops
Department/ Agency |  |  | : | Department of the Interior and Local Government (DILG)
Implementing Entity |  |  | : | DOST-Local Government Academy (LGA)
Implementation Period |  |  | : | July to December 2022
Required Budget
I. | Maintenance and Other Operating Expenses
Training and Scholarship Expenses
|  | Training Expenses |  |  |  | 1330000
Supplies and Materials Expenses (itemized based on GAM)
| Office Supplies Expenses, Gasoline, Oil and Lubricants Expenses | Office Supplies Expenses |  |  |  | 30000
Other Maintenance and Operating Expenses (itemize based on GAM)
|  | Representation Expenses |  |  |  | 6000
|  |  |  | Sub-Total for MOOE |  | 1366000
II. | Capital Outlay
Machinery and Equipment
|  | Information and Communications Technology Equipment |  |  |  | 20000
|  |  |  | Sub-Total for CO |  | 20000
|  |  |  | GRAND TOTAL |  | 1386000
(To be filled-out by NIC Secretariat )
[5 empty] | Amount | TOTAL
* | Chargeable against the FY ____ Fund |  |  |  | 0
Certified Correct: |  |  |  | Endorsed By: |  | Approved By:
NIC Secretariat Staff (Position) |  |  |  | NIC Secretariat Executive Director |  | Chairperson of the NIC Executive Technical Board
NIC Secretariat Screening: _____________________
III.
*